## Tasks
Task | Priority | Status | Start date | End date | Milestone | Deliverable | Notes
Analyze existing apps (PocketGuard, EveryDollar) | P1 | In progress | 2025-10-06 | 2025-10-13 | Gap anlysis completed | Competitive Analysis | Identify missing features like customizable categories
Set up development environment (Python, Flask, React) | P3 | In progress | 2025-10-06 | 2025-10-10 | Environment Ready | https://github.com/RodActual/SmartBudget-MVP | Install IDEs, libraries, and frameworks | LEGEND
Research user needs and pain points | P3 | In progress | 2025-10-06 | 2025-10-10 | Research summary completed |  | Surveys or interviews with target users
Sketch initial dashboard layout | P1 | In progress | 2025-10-13 | 2025-10-17 | Low-fidelity wireframes ready |  | Focus on usability and navigation
Define MVP features | P3 | Completed | 2025-10-13 | 2025-10-17 | MVP feature list finalized | Features Sheet | Core functionality to track expenses and alerts
Learn database basics (Firebase) | P1 | Not started | 2025-10-20 | 2025-10-24 | Database knowledge ready |  | Understand tables, schemas, and CRUD operations
Create high-fidelity dashboard mockups | P1 | Not started | 2025-10-20 | 2025-10-31 | UI design ready |  | Include charts, alerts, and category system
Design database schema | P3 | Not started | 2025-10-20 | 2025-10-24 | Schema approved |  | Supports expense tracking, categories, and alerts
Implement basic backend structure | P3 | Not started | 2025-10-27 | 2025-11-07 | Backend skeleton ready |  | Set up routes, database connections, and models
Implement basic frontend structure | P3 | Not started | 2025-10-27 | 2025-11-07 | Frontend skeleton ready |  | Initial pages and navigation
Implement CRUD for expense entries | P3 | Not started | 2025-11-03 | 2025-11-14 | MVP can store expenses |  | Core tracking functionality (Q1 feature)
Add automated expense categorization | P2 | Not started | 2025-11-10 | 2025-11-17 | Expenses categorized automatically |  | Q1 feature; reduces manual work
Implement customizable categories | P2 | Not started | 2025-11-10 | 2025-11-17 | Users can add/edit categories |  | Q1 feature; supports personalization
Integrate visual charts for spending | P1 | Not started | 2025-11-17 | 2025-11-24 | Charts display expenses |  | Q2 feature; provides spending insights
Build alert system for overspending | P2 | Not started | 2025-11-17 | 2025-11-24 | Basic alert notifications active |  | Q1 feature; encourages better habits
Add personalized savings goals | P3 | Not started | 2025-11-24 | 2025-11-28 | Goals functionality added |  | Q2 feature; optional for MVP
Collect internal testing feedback | P3 | Not started | 2025-11-24 | 2025-11-28 | MVP tested | Rodriguez Feedback Log | Test functionality and usability
Prepare documentation for MVP | P1 | Not started | 2025-12-01 | 2025-12-07 | Documentation drafted |  | User guide, screenshots, and technical notes
Plan future enhancements | P1 | Not started | 2025-12-01 | 2025-12-07 | Feature roadmap ready |  | Q3–Q4 features for post-MVP planning
Refine UI and fix bugs | P3 | Not started | 2025-12-01 | 2025-12-05 | MVP polished |  | Minor UX and functionality improvements
Note on J3: Priority (0–3): 0 = Low – Nice-to-have features; optional 1 = Medium – Useful but not critical; can be added after MVP 2 = High – Important for usability; should be included if feasible 3 = Critical / Must-have – Essential for MVP; cannot be skipped Milestone: A measurable checkpoint showing the completion of a key task or feature Notes: Additional context, dependencies, or instructions for the task

## Features
Feature | Category | Status | Size | Launch | Notes
Expense tracking (CRUD) | Category 1 | Not started | M | Q1 | Core functionality; essential for MVP | LEGEND
Automated expense categorization | Category 2 | Not started | M | Q1 | Improves usability; reduces manual work
Customizable categories | Category 2 | Not started | M | Q1 | Allows users to personalize budgets
Spending alerts | Category 1 | Not started | S | Q1 | Encourages better financial habits
Visual charts / reports | Category 3 | Not started | M | Q2 | Helps users understand spending trends
Personalized savings goals | Category 3 | Not started | M | Q2 | Optional for MVP; motivates users
Real-time spending suggestions | Category 2 | Not started | L | Q2 | Provides actionable advice; can improve habit formation
Recurring transaction tracking | Category 4 | Not started | L | Q3 | Nice-to-have; supports ongoing budgeting
Exportable reports | Category 4 | Not started | S | Q3 | Useful for advanced users
Bank API integration | Category 4 | Not started | XL | Q4 | High effort; automates data input
Note on H2: Explanation of columns: Category 1–4: 1 = Critical/Must-have, 2 = High Value, 3 = Medium Value, 4 = Low Value/Optional Size XS–XXL: XS = very small task, XXL = very large/complex task Launch Q1–Q4: Q1 = early MVP, Q2/Q3 = subsequent enhancements, Q4 = final refinements or optional features Notes: Additional context, dependencies, or instructions for the task

## NFRs
Feature | Measurement/Standard | Category | Status | Size | Launch | Notes
System response time for dashboard loading shall not exceed 3 seconds. | ≤ 3 seconds | Performance | Not started | M | Q1 | Core performance requirement for MVP. | LEGEND
Expense categorization must complete within 2 seconds after submission. | ≤ 2 seconds | Performance | Not started | M | Q1 | Must feel instant to the user for good UX.
All frontend-backend communication uses HTTPS. | TLS 1.2+ encryption | Security & Integrity | Not started | XS | Q1 | Must-have for secure MVP deployment.
Authentication uses Firebase Auth for credential management. | OAuth 2.0 compliance | Security & Integrity | Not started | S | Q1 | Core login security feature.
API keys and tokens stored in environment variables. | Secure environment config | Security & Integrity | Not started | XS | Q1 | Simple, high-priority configuration task.
Interface is intuitive and responsive on desktop/mobile. | Meets WCAG 2.1 AA | Usability & Maintainability | Not started | M | Q1 | High usability focus for MVP release.
Core actions (add expense, view dashboard) accessible within 2 clicks. | 2-click rule | Usability & Maintainability | Not started | S | Q1 | Core user flow requirement.
Codebase follows modular architecture (frontend/backend separation). | Verified via structure | Usability & Maintainability | Not started | L | Q1 | Foundation for clean project structure.
Validate all expense and goal data before saving. | Input validation checks | Security & Integrity | Not started | S | Q1 | Prevents incorrect or malicious input.
Charts and summaries refresh in real time when new data is added. | Real-time update | Performance | Not started | L | Q2 | Enhances interactivity; secondary feature post-MVP.
Maintain 99% system uptime. | 99% monthly availability | Scalability & Reliability | Not started | M | Q2 | Target for hosted environment stability.
All code includes inline documentation and comments. | ≥ 80% comment coverage | Usability & Maintainability | Not started | M | Q2 | Improves maintainability and grading documentation.
Enable GitHub version control and CI/CD integration. | Auto-deployment verified | Usability & Maintainability | Not started | L | Q2 | Ensures consistency for future updates.
App runs on Chrome, Edge, Safari, Firefox without plugins. | Browser compatibility test | Usability & Maintainability | Not started | M | Q2 | Cross-platform requirement for wide accessibility.
Backend deployable to Replit, Render, or Firebase Hosting. | Deployment verification | Usability & Maintainability | Not started | L | Q2 | Simplifies hosting and demonstration.
Transactions must be atomic (no partial writes). | Transaction logs consistent | Security & Integrity | Not started | M | Q2 | Ensures database consistency.
Log API requests with timestamp and response code. | Log audit record | Security & Integrity | Not started | S | Q2 | Enables debugging and monitoring.
Store error logs securely without user data. | Log security audit | Security & Integrity | Not started | S | Q2 | Prevents data leaks during debugging.
System supports up to 1,000 active users without performance degradation. | Load test at 1,000 users | Scalability & Reliability | Not started | L | Q3 | Important for scale testing after MVP.
Backend architecture allows horizontal scaling via Flask + Firebase APIs. | Load-balanced design | Scalability & Reliability | Not started | L | Q3 | Enables future expansion and cloud hosting.
Store unsynced data locally and auto-sync once reconnected. | Offline data persistence | Scalability & Reliability | Not started | L | Q4 | Improves reliability for mobile or low connectivity.
Note on I2: Explanation of columns: Size XS–XXL: XS = very small task, XXL = very large/complex task Launch Q1–Q4: Q1 = early MVP, Q2/Q3 = subsequent enhancements, Q4 = final refinements or optional features Notes: Additional context, dependencies, or instructions for the task